## WorkSheet (hidden)
G | List for Validation
Y
R
Return

## APQP Front Sheet
0
| Navistar Advanced Product Quality Planning - Worksheet and Report | [8 empty] | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
| Customer: |  | Navistar Inc. |  | Program: |  |  |  |  | Report Date: | 2022-04-11 | APQP Summary | Percentage
| Supplier Name: |  |  |  | Part Name: |  |  |  |  | Part Number: |  | % Elements Complete Compared to Plan | 0%
| Supplier Team Members |  | Responsibility |  |  |  | Date for the Team |  |  |  |  | % Elements to Plan | 0%
[7 empty] | Entering the Team |  | Leaving the Team |  | Email / Phone
[12 empty] | % Elements at Risk | 0%
[12 empty] | % Elements Delayed Compared to Plan | 0%
User Notes
Scoring guideline: R = Elements delayed compared to plan, Y = Risk to target, G = on target, B = complete
| Customer Contact Names |  | Responsibility |  |  |  | Entering the Team |  | Leaving the Team |  | Email / Phone
Report Date must be entered for Current, Last, and Trend columns to populate.
Text in this format is a hyperlink to another section within the document.
Text in columns E, F, & G are from another section and password protected on this sheet.
| APQP Element |  |  | GYR Status |  |  | Program Need Date | Planned Date | Closed Date | Resp. Initials | Remarks
|  |  |  | Current | Last | Trend
| 1 | Design Review
| 2 | Drawings and Specifications
| 3 | Preliminary Bill of Materials
| 4 | Design Failure Mode Analysis (DFMEA)
| 5 | Design Verification Requirements
| 6 | Design DVP&R
| 7 | Design Verification Test Review
| 8 | Preliminary Process Flow Diagram
| 9 | Utilities Plan, Layout Plan & Manpower Plan
| 10 | Tooling and Inspection Equipment
| 11 | Prototype Process Flow Chart, FMEA, Control Plan
| 12 | Logistics and Packaging Internal / External
| 13 | Pre-Production Process Flow Diagram, PFMEA, CP
| 14 | Production Test and Measuring Equipment
| 15 | Planned Maintenance and Key Spares Requirement
| 16 | Process PPAP and Capacity Planning
| 17 | Sub-Supplier Selection - Direct Materials
| 18 | Sub-Supplier - Capital Equipment and Tooling
| 19 | Sub-Supplier Program Staus Matrix
| 20 | Pre-Production Process Flow Diagram
| 21 | Tooling
| 22 | Pre-Production Control Plan
| 23 | Operator Inspection / Process Instructions
| 24 | Preliminary Capability Studies
| 25 | Production Test and Measuring Equipment
| 26 | Document Review
| 27 | Process Capacity Sign-off
| 28 | Product and Process Sign-off (Phase-1 Parts)
| 29 | Product and Process Sign-off (Phase-2 Parts)
| 30 | Sub-Supplier - Direct Materials
|  | Program Milestones Must Be On Timing Plan | Approvals : |  |  | Program Manager |  |  |  | Date
[6 empty] | Quality Representative |  |  |  | Date
[6 empty] | Customer Representative |  |  |  | Date

## Kick Off Meeting
APQP Kickoff Meeting | [13 empty] | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
This document should be completed by the Supplier and provided to the SQE/SDM prior to the meeting date.
Part number(s): | [14 empty] | Date:
Part Description: | [13 empty] | Supplier Code:
Supplier Name: | [8 empty] | X |  | Supplier Location:
SECTION 1 - CUSTOMER REQUIREMENTS
1.1 |  |  | Yes | No | Does the Supplier understand all the applications and intended end uses of the parts/materials for all customers?
Explain:
1.2 |  |  | Yes | No | Does the Supplier have the latest information about program timing (examples include Drawing release, Prototype, PPAP date, Build date, Material required at plant date, Start of Production, Volumes)?
Explain:
Review Key Project Milestones with Supplier:
|  | Key Project Milestone |  |  |  | Date |  |  |  |  | Key Project Milestone |  |  |  |  | Date
1.3 |  |  | Yes | No | Does the Supplier have copies of the latest versions of and understand the ISO 9001 and, if applicable, IATF 16949 quality management standards, the AIAG manuals (APQP, PPAP,FMEA, SPC, MSA) and, where appropriate, the AIAG CQI special process manuals?
Explain:
1.4 |  |  | Yes | No | Does the Supplier have and understand all the requirements listed in the Navistar Integrated Supplier Quality Requirements, Navistar forms, and other Navistar requirements (e.g. appearance item approval and MPAPS B-50)
Explain:
1.5 |  |  | Yes | No | Does the Supplier understand the requirements of Navistar Packaging Specification D-13?
Explain:
1.6 |  |  | Yes | No | Are returnable containers required?
Explain:
1.7 |  |  | Yes | No | Are there any packaging issues left to resolve (such as alternative packaging, dunnage, protective sleeves)?
Explain:
1.8 |  |  | Yes | No | Is the Supplier ready to receive Navistar EDI orders?
Explain:
1.9 |  |  | Yes | No | Does the supplier understands Navistar Cybersecurity Requirements (Cyber-4_CSD0005 & Cyber-9_CSD0011)?
Explain:
1.1 |  |  | Yes | No | Does the supplier understand the Requirements for completing the assessment of the Navistar Cybersecurity Requirements?
Explain:
1.11 |  |  | Yes | No | Does the supplier understands Navistar Network Requirements (VSR-C, VSR-D, VSR-UDS)?
Explain:
1.12 |  |  | Yes | No | Does the supplier understands the Requirements for completing the assessment of the Navistar Network Requirements?
Explain:
1.13 |  |  | Yes | No | Is the organization aligned with ASPICE structure processes?
Explain:
SECTION 2 - PRODUCT DESIGN / DEVELOPMENT
2.1 |  |  | Yes | No | Does the Supplier have and understand ALL of the latest drawings and specifications, including MPAPS B-50?
Explain:
2.2 |  |  | Yes | No | If Navistar is design responsible, has a Design-FMEA review been completed with the Supplier and the Navistar Engineer and records of review are available?
Explain:
2.6 |  |  | Yes | No | Are there any Pre-Prototype/Prototype requirements?
Explain:
List them below:
[5 empty] | Prototype Material Required Date | Quantity |  |  |  |  | Supplier Promise Date
2.7 |  |  | Yes | No | Does the Supplier understand the requirements of the Navistar procedure (with Phased PPAP) for prototype parts and the requirement that prototype parts must be inspected, verified and validated that they meet design intent?
Explain:
2.8 |  |  | Yes | No | Will the appropriate control plan be developed for use during each build (e.g. NPD build events, Prototype, Pre-Launch, and Production)?
Explain:
2.9 |  |  | Yes | No | Does the supplier understands the requirements to provide Navistar with their software release content and timing plan?
Explain:
2.1 |  |  | Yes | No | Does the supplier understands the requirements to review the requirements, design, and software DVP of software changes?
Explain:
SECTION 3 - PROCESS DESIGN/DEVELOPMENT
Key Activities from the APQP Project Plan
3.1 |  |  | Yes | No | Has the Supplier filled out, updated and submitted the Navistar APQP workbook, and Timing Plan for these parts?
Explain:
3.4 |  |  | Yes | No | Are any new equipment, tooling, gages, special fixtures or test equipment needed to produce this part?
Explain:
3.6 |  |  | Yes | No | Has the Supplier confirmed that their subcontractors will do the following?: APQP
Explain:
3.7 |  |  | Yes | No | Has the Supplier confirmed that their subcontractors will do the following?: PPAP
Explain:
3.8 | Enter lead time for tooling (wks): | [6 empty] | 3.12 |  | Enter number of Cavities / Molds to submit for PPAP:
3.9 | Enter date for first production run & submission of PPAP: | [6 empty] | 3.13 |  | Enter number of Cavities / Molds to submit for PPAP:
3.1 | Enter estimated PPAP Submission Date: | [6 empty] | 3.14 |  | Enter number of parts per Cavity / Mold in PPAP production run:
3.11 | Submission Level (1- 5) | [6 empty] | 3.15 |  | Enter the name of the person you will submit PPAP to:
SECTION 4 - RUN @ RATE & CAPACITY RELATED
4.1 |  |  |  |  | A. Daily Contracted Capacity | [6 empty] | E. Number of work hours per day
[5 empty] | B. Number of tool sets required | [6 empty] | F. Number of shifts per day
[5 empty] | C. Number of machines/lines/cells required | [6 empty] | G. Number of days per week
D. Capacity per tool set
4.2 |  |  | Yes | No | Does the Supplier understand the Navistar Capacity Planning Verification process?
Explain:
SECTION 5 – SUPPLIER QUALITY PERFORMANCE
5.1 |  |  | Yes | No | Does the Supplier understand the Navistar Global 8D requirements and are there any unresolved Global 8Ds?
Explain:
5.2 |  |  | Yes | No | Does Supplier understand the requirements for controlled shipping level 1 and 2 and Navistar Quality Top Focus program? Are any parts currently on controlled shipping status?
Explain:
5.3 |  |  | Yes | No | Does the Supplier understand the Navistar Change Management requirements, Supplier Request for Change Authorization (SREA), and the Navistar Deviation process?
Explain:
5.5 |  |  |  |  | What is the Suppliers current R/1000 or PPM for current customers with similar products: | [11 empty] | PPM | R/1000
Explain:
Navistar Attendees: | [6 empty] | Date: | [5 empty] | Supplier Attendees:
Advanced Supplier Quality Engineer | [12 empty] | Plant Quality Manager
Product/Design Release Engineer | [12 empty] | Quality Manager
Supply Manager | [12 empty] | Program Manager
Materials Representative | [12 empty] | Manufacturing Engineer
Quality Engineer

## Design
G
Y
R
B
| Design |  |  |  | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
| If NOT APPLICABLE Element is left blank |  | Status GYR |  |  |  | Target Date for Completion
| Project Element | Key Requirements | Current | Last | Comments | Resp. Initials
| 1) | Design Review |  |  | Element Responsibility:
| 1.1 | Have all design changes been incorporated into the latest specifications and drawings?
| 1.2 | Do design changes have an impact on the timing plan and the customer Material Required Dates?
Software Review (If applicable)
| 1.3 | Have all software changes been review with Controls and Software SMT?
| 1.4 | Have all software changes been formalized in a Software Change Request?
| 2) | Drawings and Specifications |  |  | Element Responsibility:
(received from Navistar)
| 2.1.1 | Is a complete set of drawings (schematic, mechanical, layout) available and released for the latest level product?
| 2.1.2 | Does the supplier have the latest specification and test requirements for hardware and software? Where appropriate, have these been flowed down to the sub-suppliers?
| 2.1.3 | Is the Design required to be compliant with any Government Regulation?
| 2.1.4 | Have 'Special Characteristics', such as KCC, KPC, CC, and SC been identified/agreed to?
Manufacturing
| 2.2.1 | Has the Feasibility Commitment been completed and signed as evidence of that the product can be produced?
Required Specifications
| 2.3.1 | If listed on drawing/blueprint, have all DR's listed on the blueprint been reviewed to identify special characteristics and PPAP requirements?
| 2.3.2 | If listed on drawing/blueprint, have all Navistar specifications (such as MPAPS requirements) been reviewed for special characteristics and PPAP requirements?
| 2.3.3 | If listed on drawing/blueprint, have all Industry specifications (such as DIN standards) been reviewed for special characteristics and PPAP requirements?
Software content and timing (If applicable)
| 2.4.1 | Have the Software Specifications been provided to/from Navistar?
| 2.4.2 | Is the Software Content and Timing Plan available and approved by Controls SMT?
Software Manufacturing and Service Impacts (If applicable)
| 2.5.1 | Does the new software / software change has an impact to Navistar Manufacturing or Navistar Service?
| 2.5.2 | Does the new software / software change introduce any new programmable parameters?
| 2.5.3 | Does the new software / software change introduce any new faults?
| 2.5.4 | Does the new software / software change require new programming tools or update of current programming tools?
| 2.5.5 | Is the new software / software change backwards compatible (if running change)?
Govermental and Navistar Required Specifications for software (If applicable)
| 2.6.1 | Does the new software / software change have an impact on Governmental Regulations such as CARB, EPA, NTSA, FMVSS, etc.
| 2.6.2 | Does the new software / software change have exceptions or introduce any new exceptions to Navistar DRD requirements?
| 3) | Preliminary Bill of Materials |  |  | Element Responsibility:
| 3.1 | Is the Bill of Materials complete and costed, Does it meet the business target?
| 3.2 | Are component standards defined?
| 3.3 | Is the BOM full volume capable?
| 3.4 | Is the BOM available and released?
| 4) | DFMEA |  |  | Element Responsibility:
| 4.1 | Has the initial DFMEA been compiled. Are the functions needed reviewed by a Cross-Functional team?
| 4.2 | Have Regulatory Requirements been included in the DFMEA, if applicable?
| 4.3 | Have Customer Potential Significant and Potential Critical Characteristics / Key Characteristics been identified?
| 4.4 | Are risks identified for meeting durability and reliability goals. Where identified are plans in place to reduce risks?
| 4.5 | Is there an action priority rating available per AIAG VDA PFMEA (formelly referred to RPN?
| 4.6 | Has the DFMEA been reviewed after design and / drawing revisions?
Software Controls System FMEA (If applicable)
| 4.7 | Has the Controls Detection identified on the System DFMEA been incorporated into the Software Plan.
| 5) | Design Verification Requirements |  |  | Element Responsibility:
| 5.1 | Is the design in accordance with the functional requirements?
| 5.2 | Is a complete set of drawings (schematic, mechanical, layout) available?
| 5.3 | Are there any further design changes planned?
| 5.4 | Are there any unproven new technologies or design features?
| 5.5 | Are there any new manufacturing processes required?
| 5.6 | Have special characteristics been identified?
| 5.7 | Has a Tabulated Design Verification Plan (DVP) been completed and approved by Navistar Engineering?
| 6) | Design DVP&R |  |  | Element Responsibility:
| 6.1 | Does the DVP&R TEST plan meet the customer requirements?
| 6.2 | Has DV testing passed successfully?
| 6.3 | Do the DV results meet the customer specification requirements?
| 6.4 | Are failed items during production validation testing covered by corrective actions (8D); are corrective actions verified and retested?
| 6.5 | Does the DVP&R content include all required specifications and standards specified on the drawing, CAD Model, and/or in the Design Requirements Document (DRD), including FMVSS and/or other regulatory requirements?
| 7) | Design Verification Test Review |  |  | Element Responsibility:
| 7.1 | Are the drawings / specifications / BOM released?
| 7.2 | Are test parts representative of a production source?
| 7.3 | Have all specifications and drawings been agreed by the production source?
| 7.4 | Are the chosen designs and processes capable of mass production?
| 7.5 | Is the Design now frozen or are further tests required?
Software Verifications (If applicable)
| 7.6 | Has the Software DVP&R been reviewed and signoff by Controls SMT?
| 7.7 | Are there any software Test Cases that will require Navistar Validation beyond Supplier DVP&R?

## Plant+Process
G
Y
R
B
| Plant + Process |  |  |  | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
| If NOT APPLICABLE Element is left blank |  | Status GYR |  |  |  | Target Date for Completion
| Project Element | Key Requirements | Current | Last | Comments | Resp. Initials
| 8) | Preliminary Process Flow Diagram |  |  | Element Responsibility:
| 8.1 | Does the flow chart show all operations, control points from receiving to shipping; Is the planned manufacturing flow adequate and without major risk?
| 8.2 | Are critical processes, control points for customer designated characteristics and / or critical processes / product characteristics included and highlighted?
| 9) | Utilities Plan, Layout Plan & Manpower Plan |  |  | Element Responsibility:
| 9.1.1 | Does the floor plan have clearly marked areas for all materials, tools, and equipment at each operation?
| 9.1.2 | Has sufficient space been allocated for all equipment?
| 9.1.3 | Will there be adequate services (e.g. electricity, compressed air) available on time?
| 9.1.4 | Have controls been established to eliminate the potential for an operation, including outside processing, to contaminate or mix similar products?
| 9.1.5 | Is material protected from overhead or air handling systems contamination?
| 9.1.6 | Are inspection points logically located; adequate for staging and hold areas?
| 9.1.7 | Is there a recruitment and training plan that meets the needs of ramp-up, and production processes at full 'run at rate' that includes quality inspection and maintenance support?
| 9.1.8 | Is there a training matrix by employee skill level showing numbers and training required?
Capital Equipment Plan
| 9.2.1 | Is the timing plan for new manufacturing equipment developed, reviewed and monitored?
| 9.2.2 | Does the procurement and installation meet the customer timing requirements?
| 9.2.3 | Have purchase orders been approved and released?
| 9.2.4 | Are run off with intended production rates scheduled and carried out at equipment suppliers. Results meet capacity and quality targets?
| 9.2.5 | Does run off at manufacturing installation meet the process parameters as defined at production rates scheduled?
| 9.2.6 | Have capability studies been scheduled and carried out at manufacturing site, measurements done in representative quantities, with results that meet the customer requirements?
| 10) | Tooling and Inspection Equipment |  |  | Element Responsibility:
| 10.1.1 | Is the timing plan for new tooling developed, reviewed and monitored?
| 10.1.2 | Does the procurement and installation meet the customer timing requirements?
| 10.1.3 | Have purchase orders been approved and released?
| 10.1.4 | Does timing include try out and optimization?
| 10.1.5 | Have capability studies been scheduled and carried out at manufacturing site, measurements done in representative quantities, with results that meet the customer requirements?
| 10.1.6 | Is try out and optimization complete?
Measuring and Test Equipment
| 10.2.1 | Is all measuring and test equipment identified (hardware and software), is it included in the timing plan?
| 10.2.2 | Have all test and measurement equipment requirements been defined and communicated to suppliers?
| 10.2.3 | Is the procurement and installation of measurement equipment on time?
| 11) | Prototype Process Flow Chart, FMEA, Control Plan |  |  | Element Responsibility:
| 11.1.1 | Does the flow chart show all operation, control points from incoming goods to dispatch; Is the planned manufacturing flow adequate and without major risk?
Prototype Process FMEA
| 11.2.1 | Is the Process FMEA started, are the functions needed part of the FMEA team
| 11.2.2 | Does the match the Process Flow?
Prototype Control Plan
| 11.3.1 | Does the control plan include the customer special characteristics as applicable?
| 11.3.2 | Does the control plan match the Process Flow and PFMEA
| 11.3.3 | Are sample sizes for dimensional measurements, material and functional tests adequate for prototype builds?
| 12) | Logistics and Packaging Internal / External |  |  | Element Responsibility:
| 12.1.1 | Is the customers schedule known and understood?
| 12.1.2 | Does the delivery frequency agree with the customer RFQ?
| 12.1.3 | Has a transport provider been agreed?
| 12.1.4 | If required; Has a Logistics FMEA been completed, and updated?
| 12.1.5 | Has internal transport, WIP controls, storage space, etc. been defined?
Packaging Internal / External
| 12.2.1 | Has a packaging and logistics trial been scheduled to assess risk for handling, cleanliness, damage, identification and procurement costs?
| 12.2.2 | Will sufficient packaging be available for a significant production run and support full volume production?
| 12.2.3 | Has a packaging / labeling specification been raised, agreed and released by the Customer?
Safety and Environment
| 12.3.1 | Are there any customer or regulatory requirements for the notification of hazardous substances e.g. MSDS and IMDS requirements?
| 12.3.2 | Has Navistar MPAPS B-50 been taken into account during product and process design?
| 13) | Pre-Production Process Flow Diagram, PFMEA, CP |  |  | Element Responsibility:
| 13.1.1 | Does the flow chart show all operation, control points from incoming goods to dispatch; Is the planned manufacturing flow adequate and without major risk?
| 13.1.2 | Are additional checks in place for pre-launch activities for critical processes, control points for customer designated characteristics and / or critical processes / product characteristics included and highlighted?
| 13.1.3 | Is there a manufacturing floor plan showing where the equipment, material flow is located in the manufacturing site?
Pre-Production Process Failure Mode Analysis
| 13.2.1 | Does the PFMEA track the Production Flow diagram to support additional inspection and test during launch?
| 13.2.2 | Is there an action priority rating available per AIAG VDA PFMEA (formelly referred to RPN? Is the severity ranking consistent with the DFMEA and the customer special characteristics?
| 13.2.3 | Have corrective actions been defined, reviewed and verified?
| 13.2.4 | Are 8D activities that have resulted from CV and DV testing been captured on the PFMEA. Have the corrective actions been verified, validated and RPN's re-scored?
| 13.2.5 | Are Special Characteristics, Pass Through and Weak Detection Characteristics been identified in the PFMEA?
Pre-Production Control Plan
| 13.3.1 | Does the pre-launch Control Plan include additional activities such as increased inspection, in-process and final check points?
| 13.3.2 | Are these addition pre-launch controls monitored by SPC or 100% inspection for customer Special Characteristics?
| 13.3.3 | Does the Control Plan track the process steps in the Process Flow chart and the PFMEA?
Special Process Planning
| 13.4.1 | If heat trieatment is involved, has the AIAG CQI-9 Heat Treat standard been used to develop the process control plan?
| 13.4.2 | If plating is involved, has the AIAG CQI-11 Plating standard been used to develop the process control plan?
| 13.4.3 | If coating is involved, has the AIAG CQI-12 Coating System standard been used to develop the process control plan?
| 13.4.4 | If welding is involved, has the AIAG CQI-15 Welding Systems standard been used to develop the process control plan?
| 13.4.5 | If Soldering is involved, has the AIAG CQI-17 Soldering Systems standard been used to develop the process control plan?
| 13.4.6 | If molding is involved, has the AIAG CQI-23 Molding Systems standard been used to develop the process control plan?
| 13.4.7 | If castings are involved, has the AIAG CQI-27 Casting systems standard been used to develop the process control plan?
Preliminary Capability Studies
| 13.5.1 | Have short term studies been carried out that provide statistical data to show process capability for use in creating PFMEA and Control Plan?
| 14) | Production Test and Measuring Equipment |  |  | Element Responsibility:
| 14.1 | Has test and measuring equipment been identified, is it included in the timing plan and progress being monitored?
| 14.2 | Have all test and measurement requirements been defined and communicated to the suppliers?
| 14.3 | Is procurement and installation of test and measurement equipment on time?
| 15) | Planned Maintenance and Key Spares Requirement |  |  | Element Responsibility:
| 15.1 | Has all production equipment and tooling been included in the PM program?
| 15.2 | Have all key spares been identified that ensure production is optimized to prevent show stoppers?
| 15.3 | Are manning and necessary trained personnel available to maintain volume production?
| 16) | Process PPAP and Capacity Planning |  |  | Element Responsibility:
| 16.1.1 | Can customers peak planned capacity be achieved at representative production runs and at costed rates?
| 16.1.2 | Has forecasted capacity verification been submitted to the customer buyer?

## Sub-Supplier
G
Y
R
B
| Sub-Supplier |  |  |  | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
| If NOT APPLICABLE Element is left blank |  | Status GYR |  |  |  | Target Date for Completion
| Project Element | Key Requirements | Current | Last | Comments | Resp. Initials
| 17) | Sub-Supplier Selection - Direct Materials |  |  | Element Responsibility:
| 17.1.1 | Has a Sub-supplier been selected, are parts identified?
| 17.1.2 | Have long lead and high risk suppliers been identified, has a plan to manage them been developed?
| 17.1.3 | Have all specifications and drawings been raised, completed and released?
Sub Supplier Selection - Prototypes
| 17.2.1 | Has a Sub-supplier been selected, to build outsourced Prototype Parts?
| 17.2.2 | Have current manufacturing drawings been issued internally and Sub-supplier plant?
| 17.2.3 | Has a manufacturing feasibility commitment been agreed that the Prototype design can be manufactured, assembled, meet required material dates and quantities?
| 18) | Sub-Supplier - Capital Equipment and Tooling |  |  | Element Responsibility:
| 18.1.1 | Is a capital equipment timing plan developed, monitored?
| 18.1.2 | Have capital equipment suppliers been identified and documented?
| 18.1.3 | Have long lead and high risk suppliers been identified, has a plan to manage them been developed?
18.1.4 | 18.1.4 | Have capital equipment specifications (including capability requirements) been raised and released?
| 18.1.5 | Are try-out schedules at supplier / manufacturing site agreed and understood.
| 18.1.6 | Where applicable, are suppliers APQP status to plan?
Sub Supplier - Tooling
| 18.2.1 | Has a tooling timing plan been developed, monitored?
| 18.2.2 | Have tooling suppliers been identified and documented?
| 18.2.3 | Have long lead and high risk suppliers been identified, has a plan to manage them been developed?
| 18.2.4 | Have tooling equipment specifications (including capability requirements) been raised and released?
| 18.2.5 | Where applicable, are suppliers APQP status to plan?
| 19) | Sub-Supplier Program Status Matrix |  |  | Element Responsibility:
| 19.1 | Are the Special Characteristic requirements known and understood by the Sub-Suppliers?
| 19.2 | Are the Pass Through and Weak Detection Characteristics requirements known and understood by the Sub-Suppliers?
| 19.3 | Has Sub-Supplier completed all actions listed on Sub-Supplier Program Staus Matrix worksheet.

## Sub-Supplier Matrix
Sub-Supplier Program Status Matrix
Sub-System/Sub-Assembly: | [5 empty] | Program(s):
SQE: | [5 empty] | Date: |  |  |  | Revision:
Tier 1 Supplier / Plant: | [5 empty] | Tier 1 Supplier Key Contact: | [6 empty] | Audit for Processes Used
Directed Buy (yes/no) | Subcontractor | Subcomponent | Status / GYR | Facilities: Greenfield / Transplant Y/N | If Yes, % Complete | Prod. Tooling Complete Plan Date | % Prod. Tool Complete | PTC and WD Date | PPAP Date | PPAP Status & Comments | Run @ Rate Date | Run @ Rate Status | AIAG Heat Treat Audit CQI 9 Completed | AIAG Plating Audit CQI 11 Completed | AIAG Coating Audit CQI 12 Completed | AIAG Welding Audit CQI 15 Completed | AIAG Soldering Audit CQI 17 Completed | AIAG Molding Audit CQI 23 Completed | AIAG Coating Audit CQI 27 Completed
* This document should be reviewed at all Gate Reviews for all sub-components.

## Launch Readiness Review
G
Y
R
B
| Launch Readiness Review |  |  |  | ISQ-005-FO Rev: D Date: 02/21/2022 Copies must be verified for latest revision
| If NOT APPLICABLE Element is left blank |  | Status GYR |  |  |  | Target Date for Completion
| Project Element | Key Requirements | Current | Last | Comments | Resp. Initials
| 20) | Pre-Production Process Flow Diagram |  |  | Element Responsibility:
| 20.1 | Have you confirmed that the Process Flow Diagram accurately documents all operations, and control points from receiving to shipping; Is the planned manufacturing flow adequate and without major risk?
Utilities Plan, Layout Plan & Manpower Plan
| 20.2.1 | Have you confirmed that the floor plant equipment layout has clearly marked areas for all materials, tools, and equipment at each operation?
| 20.2.2 | Has sufficient space been allocated for all equipment?
| 20.2.3 | Have you vierified that controls are in place to eliminate the potential for an operation, including outside processing, to contaminate or mix similar products?
| 20.2.4 | Is material protected from overhead or air handling systems contamination?
| 20.2.5 | Are inspection points logically located; adequate for staging and hold areas?
| 20.2.6 | Is there a training matrix by employee skill level showing numbers and training required?
| 21) | Tooling |  |  | Element Responsibility:
| 21.1 | Have you verified that alll requried tooling has been received and does not include prototype or temporary tooling.
| 21.2 | If Navistar owned tooling, is the tooling correctly tagged as Nawistar property per Navistar requirements?
| 21.3 | Has tooling passed tryout and final adjustments.
| 21.4 | Is try out and optimization complete?
| 22) | Pre-Production Control Plan |  |  | Element Responsibility:
| 22.1.1 | Have you verified that the control plan includes special characteristics?
| 22.1.2 | Have you verified that the control plan includes the Regulatory Requirements, if applicable?
| 22.1.3 | Do special characteristics all have either SPC, or 100% in station inspeciton?
| 22.1.4 | Does the control plan match the Process Flow and PFMEA?
| 22.1.5 | Does the pre-launch Control Plan include additional activities such as increased inspection, in-process and final check points for hardware and software?
| 22.1.6 | Are these addition pre-launch controls monitored by SPC or 100% inspection for customer Special Characteristics?
Production Process Flow Diagram
| 22.2.1 | Have you verified that flow chart shows all operation, control points from incoming goods to dispatch; Is the planned manufacturing flow adequate and without major risk?
| 22.2.2 | Have you verified that rework operations can be performed within the current process flow. Re-work operations to be shown on Process Flow Diagrams
Pre-Production Process Failure Mode Analysis
| 22.3.1 | Does the PFMEA track the Production Flow diagram to support additional inspection and test during launch?
| 22.3.2 | Have you verified that Regulatory and Special Characteristics were cascaded from DFMEA to PFMEA, if applicable?
| 22.3.2 | Is there an action priority rating available per AIAG VDA PFMEA (formelly referred to RPN? Is the severity ranking consistent with the DFMEA and the customer special characteristics?
| 22.3.3 | Have corrective actions been defined, reviewed and verified?
| 23) | Operator Inspection / Process Instructions |  |  | Element Responsibility:
| 23.1 | Are work instructions complete and released?
| 23.2 | Are instructions available on how to proceed with non-conforming material; i.e. Analysis, rework, disposition of NC material / returned material?
| 23.3 | Have you verified that there is a documented set-up and changeover process. This includes: documentation of each element, timing of each element and overall process, and establishment of a baseline. Documentation tracks times, improvements, goals and ideas. Standardized method to document changes and improvements to the process.
| 23.4 | Are inspection instructions available that define checking frequencies, sample sizes, acceptance standards and test specifications?
| 23.5 | Do operator instructions include operator actions to contain product that match the control plan "reaction plan"
| 23.6 | Standardized Work Process in place to assure workers do the job the same way every time.
| 23.7 | Do operator instructions include tool change frequency and gage mastering frequency?
| 24) | Preliminary Capability Studies |  |  | Element Responsibility:
| 24.1 | Have short term studies been carried out that provide statistical data to show process capability.
| 24.2 | Have preliminary process capability studies been performed on the characteristics identified in the Control Plan.
| 24.3 | Do all part features meet 1.33 Cpk initial capability requirement?
| 24.4 | Do CC's, SC's all meet 1.67 Cpk initial capability requirement?
| 25) | Production Test and Measuring Equipment |  |  | Element Responsibility:
| 25.1 | Has test and measuring equipment been identified, is it included in the timing plan and progress being monitored?
| 24.2 | Are detailed test and inspection operator instructions available on the manufacturing site, are the operators trained in the use of instructions and recording methods?
| 24.3 | Have you verified that provisions have been made to certify and routinely calibrate measure and test equipment?
| 24.4 | Has accpetable Measurement System Analysis (MSA) been carried out on all inspection and test equipment on the control plan to evaluate product? Are all Gage R&R's less than 10%?
| 26) | Document Review |  |  | Element Responsibility:
| 26.1.1 | Has all Design Validation passed testing and been approved in writing by Navistar Engineering?
| 26.1.2 | Are all Design Validation documentation complete and DV issues / 8D's closed with countermeasures in place?
| 26.1.3 | Have all component and assembly drawings been updated and released?
| 26.1.4 | Are customer specifications complete (software and function) and requirements frozen?
| 26.1.5 | Has the software DVP&R been signed off?
| 26.1.6 | Have the desing product specifications and final sotfware files been released to Navistar Engineering?
| 26.1.7 | Has the final notes been submitted to Navistar Engineering?
| 26.1.8 | Has all production documentation been completed and released to manufacturing?
| 26.1.9 | Has the Production trial run been scheduled with adequate quantity of parts that represents Production Rates
| 26.1.10 | Have the Process Flow / PFMEA and Control Plans been completed, reviewed and approved?
| 26.1.11 | Has the Pass Thorugh Assesment and Weak Detection Matrix been reviewed and approved?
Special Process Audits
| 26.2.1 | If heat trieatment is involved, has the SQE reviewed the current AIAG CQI-9 Heat Treat Assessment at the supplier location?
| 26.2.2 | If plating is involved, has the SQE reviewed the current AIAG CQI-11 Plating Assessment at the supplier location?
| 26.2.3 | If coating is involved, has the SQE reviewed the current AIAG CQI-12 Coating System Assessment at the supplier location?
| 26.2.4 | If welding is involved, has the SQE reviewed the current AIAG CQI-15 Welding Systems Assessment at the supplier location?
| 26.2.5 | If Soldering is involved, has the SQE reviewed the current AIAG CQI-17 Soldering Systems Assessment at the supplier location?
| 26.2.6 | If molding is involved, has the SQE reviewed the current AIAG CQI-23 Molding Systems Assessment at the supplier location?
| 26.2.7 | If castings are involved, has the SQE reviewed the current AIAG CQI-27 Casting systems Assessment at the supplier location?
| 27) | Process Capacity Sign-off |  |  | Element Responsibility:
| 27.1 | Can customers peak planned capacity be achieved at representative production runs and at costed rates?
| 27.2 | Has forecasted capacity verification been submitted to Navistar?
| 28) | Product and Process Sign-off (Phase-1 Parts) |  |  | Element Responsibility:
| 28.2 | Is all Production Parts Approval Process (PPAP) documentation complete and readily available?
| 28.3 | Has Navistar signed the PSW authorizing shipment?
| 29) | Product and Process Sign-off (Phase-2 or Phase-3 Parts) |  |  | Element Responsibility:
| 29.1 | Is all Production Parts Approval Process (PPAP) documentation complete and readily available?
| 29.2 | Has Navistar signed the PSW authorizing shipment?
| 30) | Sub-Supplier - Direct Materials |  |  | Element Responsibility:
| 30.1 | Have all sub-supplier parts been PPAP approved without Interim or limited approval and without a time limit on that approval.
| 30.2 | Has the tier-1 supplier conducted capacity approval of sub-supplier parts and established capacity meets Navistar full volume requirements?
| 30.3 | Has the tier-1 supplier approved any deviations for sub-supplier parts?

## Timing Plan
PART NUMBER & DESCRIPTION | ORIGINAL DATE | time axis 2017-02-06 to 2018-04-09
REVISION DATE
|  | Planned Start | Planned Completion | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Kick-Off Meeting | Plan |  |  | 0
| Actual |  |  | 0
Design Review and Feasibility Sign-off | Plan |  |  | 0
| Actual |  |  | 0
Production Plan, PFD, PFMEA, Control Plan, Facilities, Gaging Strategy | Plan |  |  | 0
| Actual |  |  | 0
New or Additional Facilities or Capital Equipment | Plan |  |  | 0
| Actual |  |  | 0
New or Additional Tooling and Gauging | Plan |  |  | 0
| Actual |  |  | 0
Production Run, Capability and Gage R&R Established | Plan |  |  | 0
| Actual |  |  | 0
DVP&R Conducted and Completed With Navistar Approval | Plan |  |  | 0
| Actual |  |  | 0
Initial PPAP Approval | Plan |  |  | 0
| Actual |  |  | 0
Material Required Date and Actual Delivery Date | Plan |  |  | 0
| Actual |  |  | 0
PPAP Phase-3 Capacity Verifcation | Plan |  |  | 0
| Actual |  |  | 0
[6 empty] | = | ACTIVITY IS COMPLETE (COLOR LAST BLOCK OF ACTUAL TIMING)
[6 empty] | = | ACTIVITY IS ON OR AHEAD OF SCHEDULE
[6 empty] | = | ACTIVITY IS BEHIND SCHEDULE BUT WILL RECOVER TO MEET PLAN
[6 empty] | = | ACTIVITY IS BEHIND SCHEDULE BUT WILL NOT RECOVER TO MEET PLAN
Note on F1: you can enter date the week before kick-off meeting to set calendar. Chose a monday

## Example Timing Plan
PART NUMBER & DESCRIPTION | ORIGINAL DATE |  | 2017-06-21 | time axis 2017-02-13 to 2018-04-16
12345678C91 STEERING MODULE | REVISION DATE |  | 2017-10-19
|  | Planned Start | Planned Completion | Duration | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Kick-Off Meeting | Plan | 2017-06-18 | 2017-06-20 | 2 | bar: 2017-02-13
| Actual | 2017-06-20 | 2017-06-21 | 1 | bar: 2017-02-13
Design Review and Feasibility Sign-off | Plan | 2017-07-10 | 2017-07-12 | 2 | bar: 2017-03-13
| Actual | 2017-07-21 | 2017-07-23 | 2 | bar: 2017-03-20
Production Plan, PFD, PFMEA, Control Plan, Facilities, Gaging Strategy | Plan | 2017-09-02 | 2017-10-26 | 54 | bar: 2017-05-01 to 2017-06-19
| Actual | 2017-08-30 | 2017-10-12 | 43 | bar: 2017-04-24 to 2017-06-05
New or Additional Facilities or Capital Equipment | Plan |  |  | 0 | bar: 2017-06-05 to 2017-10-16
| Actual |  |  | 0 | bar: 2017-06-05 to 2017-06-19
New or Additional Tooling and Gauging | Plan | 2017-10-21 | 2018-03-24 | 154 | bar: 2017-05-01 to 2017-11-13
| Actual |  |  | 0 | bar: 2017-04-17 to 2017-06-26
Production Run, Capability and Gage R&R Established | Plan |  |  | 0 | bar: 2017-11-27 to 2017-12-11
| Actual |  |  | 0
DVP&R Conducted and Completed With Navistar Approval | Plan |  |  | 0 | bar: 2017-04-17 to 2017-07-10
| Actual |  |  | 0 | bar: 2017-04-03 to 2017-07-03
Initial PPAP Approval | Plan |  |  | 0 | bar: 2017-12-18 to 2017-12-25
| Actual |  |  | 0
Material Required Date and Actual Delivery Date | Plan |  |  | 0 | bar: 2018-02-05
| Actual |  |  | 0
PPAP Phase-3 Capacity Verifcation | Plan |  |  | 0 | bar: 2018-04-02 to 2018-04-09
| Actual |  |  | 0
[6 empty] | = | ACTIVITY IS COMPLETE (COLOR LAST BLOCK OF ACTUAL TIMING)
[6 empty] | = | ACTIVITY IS ON OR AHEAD OF SCHEDULE
[6 empty] | = | ACTIVITY IS BEHIND SCHEDULE BUT WILL RECOVER TO MEET PLAN
[6 empty] | = | ACTIVITY IS BEHIND SCHEDULE BUT WILL NOT RECOVER TO MEET PLAN

## Revision History
Rev. No. | Effective Date | Revision History
A | 2012-11-01 | New form ISQ-005-FO for ISQ (KdW, 10/19/2012)
B | 2013-03-08 | Fixed functionality issues related to form function. Changed checkboxes to individual cells. Removed the shading. Removed PTC Analysis From and Capacity Verification Forms.
C | 2017-02-15 | Removed Early Production Capability sheet
Added Launch Readiness Review Sheet
Added requirements for CQI-9, 11, 12, 15, 17, 23, 27
D | 2022-02-21 | Added Regulatory, Software, PTC and WD related questions. Updated Color code for Scoring. Fixed functionality issues related to form function. Updated questions to be aligned with updated NSQR.